## Changelog
Date | Phase | Type | Description | Files Changed | Commit SHA | Tested | Deployed | Notes
2026-05-28 | Phase 0 | Docs | Initial planning: full SURF Intraday with 15-min cron, tier bands, timezone revert | docs/specs/ (planning only) | — | N | N | Plan locked: omni_purchase ROAS, auto% thresholds, ad_accounts.timezone column, 9-day build.
2026-05-28 | Pivot | Refactor | Scope reduced — feature replaces Raise budget 25% button on /action-needed, not standalone cron | (deleted) backend/alembic/versions/042_surf_intraday.py, backend/app/models/surf.py | — | N | N | User feedback: don't need cron/state machine; just per-click button with absolute cap. 7 tasks → 5.
2026-05-28 | Phase 1 | Migration | Add ad_accounts.raise_pct, cut_pct, max_raise_per_click_abs, max_cut_per_click_abs | backend/alembic/versions/042_budget_limits_per_branch.py; backend/app/models/account.py | — | Y | N | Postgres has CHECK constraints (raise_pct in (0,1], cut_pct in (0,1), abs >0 or NULL). SQLite tests rely on app-layer validation. Defaults preserve legacy: 0.25 / 0.50 / NULL / NULL. Smoke test 5/5 pass.
2026-05-28 | Phase 2 | Feature | /action-needed/apply reads per-branch caps, clamps delta, audits applied_cap reason | backend/app/routers/action_needed.py (_resolve_budget_change helper + apply_action rewrite) | — | Y | N | 8/8 unit cases + 5/5 existing test_action_needed.py tests pass. No-op guard added: refuses Meta call if cap binds delta to 0. action_logs.action_params now carries from/new/delta/pcts/caps/applied_cap/currency.
2026-05-28 | Phase 3 | Feature | GET + PATCH /accounts/{id}/budget-limits with admin/creator role gate + change_log audit | backend/app/routers/accounts.py (BudgetLimitsUpdate model + 2 endpoints) | — | Y | N | 7/7 TestClient checks pass: defaults, update, pydantic 422 on raise_pct>1, cut_pct≥1, send 0 clears cap, audit before/after diff, viewer role rejected. Sending 0 explicitly = clear cap (NULL).
2026-05-28 | Phase 4 | Feature | Budget Limits editor on /accounts page (expandable per Meta account) | frontend/src/app/accounts/BudgetLimitsEditor.tsx (new); frontend/src/app/accounts/page.tsx (+Limits toggle) | — | Y | N | Tsc passes clean. UX: 'Limits' button per Meta account card → expandable form with 4 fields, live preview on hypothetical 1000-unit budget showing cap clamping, Save audits to Activity Log. Google/TikTok cards hide the button (auto-apply not wired for those platforms).
2026-05-28 | Pivot 2 | UX | Settings move from /accounts inline → modal on /action-needed Apply SURF | frontend/src/app/accounts/page.tsx (reverted to original) | — | Y | N | User feedback: 'Lúc bấm nút Apply SURF thì hiện settings luôn'. /accounts editor removed; BudgetLimitsEditor.tsx kept as reusable component for the modal.
2026-05-28 | Phase 5 | Feature | SurfApplyModal: budget preview + embedded limits editor + Apply button | frontend/src/components/action-needed/SurfApplyModal.tsx (new); action-needed/page.tsx (+modal state, handleSurfApplied) | — | Y | N | Tsc clean. Modal shows current → new budget preview with cap clamping math (mirrors backend _resolve_budget_change). Apply button POSTs /action-needed/apply with applied_cap in audit. Pause campaign keeps direct confirm() path (nothing to tune).
2026-05-28 | Phase 6 | Feature | Button labels: 'Raise budget 25%' → 'Apply SURF'; 'Cut budget 50%' → 'Apply SURF (cut)' | frontend/src/components/action-needed/analysis.ts (applyOptionsFor) | — | Y | N | Pct dropped from labels since the actual delta now depends on per-branch settings — surfacing 25% would be misleading. CampaignRow type + dashboard/country/campaigns response gained account_id + daily_budget (read-only) so the modal can load branch limits + preview math.

## Phases
Phase | Subject | Status | Started | Completed | LOC | Days est | Days actual
Phase 1 | Migration 042: ad_accounts budget limit cols | Done | 2026-05-28 | 2026-05-28 | 130 | 0.25 | 0.25
Phase 2 | Backend apply_action with per-branch caps | Done | 2026-05-28 | 2026-05-28 | 120 | 0.5 | 0.5
Phase 3 | PATCH /accounts/{id}/budget-limits endpoint | Done | 2026-05-28 | 2026-05-28 | 150 | 0.5 | 0.5
Phase 4 | Frontend: dynamic labels + Settings UI | Done | 2026-05-28 | 2026-05-28 | 300 | 0.5 | 0.5
Phase 5 | Pytest fixture + Excel changelog finalize | Done | 2026-05-28 | 2026-05-28 | 150 | 0.25 | 0.25
Pivot 2 | /accounts inline editor reverted | Done | 2026-05-28 | 2026-05-28 | 50 | 0.1 | 0.1
Phase 5 | SurfApplyModal + budget preview | Done | 2026-05-28 | 2026-05-28 | 250 | 0.5 | 0.5
Phase 6 | Buttons → SURF + CampaignRow extended | Done | 2026-05-28 | 2026-05-28 | 80 | 0.25 | 0.25
TOTAL